Lab 2: Agile Backlog Creation & Sprint Simulation

Telemedicine Slot Booking & Prescription Portal — Set 1: Doctor Discovery & Slot Booking

Name / SRN: ____________________        Jira project: Telemedicine-Booking-Set1 (key TB)

# 1. Scope

This backlog is derived only from Set 1 (Doctor Discovery & Slot Booking) of the Lab 1 team work: use cases UC-01 (Search Doctor by Specialty) and UC-02 (Book Consultation Slot), requirements FR-002 and FR-003, and the UC-02 flow specification including its payment-declined alternate flow. The payment itself (UC-03) belongs to Set 2 and is only referenced as a hand-off.

# 2. Epics and User Stories

## Epic 1: Doctor Discovery

Description: Enable patients to find suitable physicians by medical specialty and see only those who actually have open consultation slots, so they can start a booking with confidence. (Source: UC-01, FR-002)

| ID | Story title | As a | I want to | So that | Priority | Pts |
| --- | --- | --- | --- | --- | --- | --- |
| Story 1.1 | Search Doctors by Specialty | a patient | search for doctors by medical specialty | I can find a physician suited to my health concern | High | 3 |
| Story 1.2 | Filter by Real-Time Availability | a patient | filter results to physicians with at least one open slot in the next 7 days | I only see doctors I can actually book | High | 5 |
| Story 1.3 | View Doctor Profile and Open Slots | a patient | view a doctor's profile and their open consultation slots | I can choose the right doctor and a suitable time | Medium | 3 |
| Story 1.4 | No-Results Guidance | a patient | see a clear message with suggestions when no doctors match my search | I can adjust my search instead of getting stuck | Low | 2 |

Epic total: 13 story points across 4 stories.

## Epic 2: Slot Booking & Reservation

Description: Let patients book a specific video consultation slot, have it held while they pay, reserved exclusively for them once payment is confirmed, and handle payment failure safely. (Source: UC-02, FR-003; includes the hand-off to UC-03 Make Payment, owned by Set 2)

| ID | Story title | As a | I want to | So that | Priority | Pts |
| --- | --- | --- | --- | --- | --- | --- |
| Story 2.1 | Select a Slot from the Booking Calendar | a patient | choose an available date and time slot for my chosen physician from a booking calendar | I can book at a time that suits me | High | 5 |
| Story 2.2 | Review Booking Summary and Confirm | a patient | review the physician, specialty, date, time and consultation fee before confirming | I am sure of the details before I pay | High | 3 |
| Story 2.3 | Temporary Slot Hold During Payment | a patient | have my chosen slot held for me while I complete payment | nobody else can take it mid-payment | High | 8 |
| Story 2.4 | Prevent Double Booking | a patient | have a booked slot disappear from all other patients' availability within 2 seconds | the same slot can never be booked by two people | High | 8 |
| Story 2.5 | Payment Hand-off and Permanent Reservation | a patient | be taken to payment and have the slot permanently reserved once payment is confirmed | my appointment is guaranteed | High | 5 |
| Story 2.6 | Booking Confirmation with Reference ID | a patient | receive a confirmation with a reference ID by email/SMS | I have proof of my appointment and its details | Medium | 3 |
| Story 2.7 | Retry After Declined Payment | a patient | retry with the same or a different payment method (up to 2 attempts) if my payment is declined | a temporary failure does not lose my booking | High | 5 |
| Story 2.8 | Release Hold and Notify on Failure | a patient | have the hold released and be told the booking was cancelled after repeated payment failure | I know the booking did not go through and the slot returns to the pool | Medium | 3 |

Epic total: 40 story points across 8 stories.

# 3. Prioritization

Priority reflects user impact. Search, availability and the core booking/reservation integrity stories are High because the portal cannot work without them. Notifications and failure cleanup are Medium. The no-results message is Low because users can still complete a booking without it.

# 4. Story Points (Fibonacci)

Points reflect relative complexity, effort and uncertainty (0, 1, 2, 3, 5, 8, 13). The two 8-point stories (2.3 slot hold, 2.4 double-booking prevention) carry the most technical risk because they involve concurrency and time-limited holds. Simple UI or messaging stories were given 2–3 points.

# 5. Sprint Plan (1 week each)

| Sprint | Stories | Points | Goal |
| --- | --- | --- | --- |
| Sprint 1 | Stories 1.1, 1.2, 1.3, 1.4, 2.1, 2.2, 2.3 | 29 | Patients can find a doctor and start a booking |
| Sprint 2 | Stories 2.4, 2.5, 2.6, 2.7, 2.8 | 24 | Booking is secure, confirmed and failure-safe |

Total backlog: 53 story points across 12 stories.

# 6. Screenshots

Insert the following Jira screenshots here before submission:

- Backlog showing both Epics and all User Stories

- Story point assignments (Epic panel or backlog view showing points)

- Active sprint board (Sprint 1 and Sprint 2)

- Burndown chart for each sprint

# 7. Reflection

### 1. Did your estimations reflect the actual effort?

[Answer after running the sprints]

### 2. Was your backlog well-prioritized?

[Answer after running the sprints]

### 3. How did your simulated sprint align with your plan?

[Answer after running the sprints]

### 4. What insights did the burndown chart give about your team’s capacity?

[Answer after running the sprints]